## Risks
ID | Risk Description | Impact (High/Med/Low) | Likelihood (High/Med/Low) | Mitigation Strategy
R1 | LLAMA model could get slow if too many users hit it at once. | High | High
R2 | Backend security might be weak. | High | High | Regular code reviews
R3 | React.js and Flask might don't work nicely together. | Medium | Low | Testing and clear documentation
R4 | MySQL could become a bottleneck as user numbers grow. | HIgh | Medium | Optimize queries

## Assumptions
ID | Assumption Description | Validation Method
A1 | MySQL database will stay clean and up to date. | Use scripts to validate and clean the data regularly.
A2 | Tuned LLAMA with right prompts can deliver relevant recommendations. | A/B test it against other models and user feedback.
A3 | Users are keen to save movies to favourite. | Track user engagement.

## Issues
ID | Issue Description | Impact (High/Med/Low) | Status (Open/In Progress/Closed) | Owner
I1 | CORS errors are popping up during local dev. | Medium | Open | Dev team
I2 | Similar movies to favourites doesn't work when not saved. | Medium | In progeress | Dev team
I3 | Recommendation not based on user history yet. | Low | Open | Dev team
I4 | We don’t have automated backups for MySQL set up yet. | High | Open | DevOps

## Dependencies
ID | Dependency Description | Why It's Needed | Status | Owner
D1 | Hosting platform (Heroku) | Deploy project. | Planned | DevOps
D2 | API endpoints | Bridge between frontend and backend. | Closed | Dev team
D3 | User authentication | Required for securely sign in. | Closed | Dev team
D4 | MySQL database schema | Required to structure data. | Closed | Dev team
D5 | Frontend user interface | Required for user interaction | Closed | Dev team